REPUBLIC OF ALBANIA                                                                                           MONTENEGRO

MINISTRY OF ENVIRONMENT, FORESTRY                                               MINISTRY OF TOURISM AND SUSTAINABLE
   AND WATER ADMINISTRATION               	                                                    DEVELOPMENT

LAKE SKADAR-SHKODRA INTEGRATED ECOSYSTEM MANAGEMENT PROJECT (LSIEMP)

PROGRESS REPORT

DECEMBER 2011

JOINT ACTIVITIES - ALBANIA AND MONTENEGRO

- Final Report on Legal Framework Review has been completed and its recommendations have been discussed in Skadar-Shkodra Lake Commission (SLC) on October 07, 2011. SLC decided to send these recommendations for further consideration and specific proposals for legal framework harmonization. The WG failed to meet after several notifications.

- LSIEMP contributed to the International Waters Conference (ICW)6 activities through participation and presentation in the conference and innovation market place with brochures and CDs as well as by hosting interested conference participants in a field trip in Lake Skadar (Montenegro side). LSIEMP presentation in both activities was rated successful.

- SLC held its meeting on October 07, 2011 in Skadar-Shkodra and some of its main decisions were:

  - SLC in cooperation with Ministries of Environment in both countries will send official letter to respective institutions and stakeholders for reconfirmation of WG members and their commitment for participation in WG meetings.

  - Until end of December 2011, the Albanian and Montenegrin Project Coordinators should inform the SLC on unallocated funds within the project having in mind its closure by end-September 2011

  - Donor meeting would be held in Montenegro before end of 2011

  - The WG on Planning and Legal should discuss and propose specific aspects of legal harmonization relevant to lake management and its protection.

  - The Predictive  Hydrological Model software will be installed in Montenegro and 1-2 persons from Albania will be trained to use and exchange information from the software. A Memorandum of Understanding (MOU) should be signed between two countries regarding the ownership of this software and who will be responsible to use it and train further specialists.

- Second donor conference will take place in Podgorica, Montenegro on December 12, 2011. All donors operating in Lake Skadar-Shkodra area have been officially invited by both Project Directors.

- Terms of Reference for the Second contract of joint Public Awareness Campaign have been submitted to the Bank. No Objection has yet to be provided.

- Contract for training on Wetland Management is not yet signed. Discussions are in process with relevant training institutions.

- Contract on the legal framework harmonization and integrating role of the SLC into national legislation is not yet signed. The recommendations of the consultancy on legal framework review were discussed in the SLC meeting on October 07, 2011 which decided to submit these recommendations for further consideration of the specific laws to be harmonizedto the WG on Planning and Legal. This meeting was not held due to several postponements from the Secretariat.

- Final report for the Joint Database for the Lake is not yet submitted. The Company has requested no cost time extension of the contract for another period of two months. The final report is expected to be submitted by………

- Draft ToRs for the last 3 targeted studies that must be identified by the WGs are not yet completed. There were no specific proposals from the WG members during this recent meeting.

- The development of Joint Lake Management Strategy including National Fishery Management Plans for each country is on-going. Inception Report submitted on July 18, 2011 was approved and Progress report is submitted in line with the project Work Plan and activity schedule, and covers the period from 12.07.-10.10.2011. Comments have been submitted by the Bank to improve the respective draft.

- Joint Lake water/ecological Monitoring Program Final report was submitted on September 15, 2011 and finally  approved during the SLC meeting held on October 7, 2011. It is important to coordinate between this developed program and the on-going relevant Lake activities.

- Predictive Hydrological Model for Lake watershed area draft Final report was submitted in September 15, 2011 and approved during the SLC meeting held on October 7, 2011. Technical training for use of the PH model took place on September 26-27 and general presentation was done on September 28, 2011 in Podgorica. Final report delivered on November 22, 2011 and approved

Issues

- The contract for investigation of Skadar/Shkodra lake water eutrophication level has not yet been signed. Three applications have been received but final decision for evaluation and contracting pending from the MoEFWA is still awaiting.

- Legal framework harmonization is pending from WG meeting, but still the AL Project Director pointed out in the SLC meeting that Albania does not have any specific proposal for harmonization of legal frameworks because legal framework in both countries is under EU Approximation.

NATIONAL ACTIVITIES-ALBANIA

- The contract for rehabilitation works of facades in the cultural heritage street of Gjuhadol in Shkodra has been signed on December 01, 2011. The works will be finished by May 30, 2012. The supervisor engineer is also contracted and on the site.

- The contract for rehabilitation works of the stream in Shiroka has been signed on December 01, 2011.  The works will be finished by May 08, 2012.

- The contract for local public awareness campaign was signed (WHEN??) and activities are ongoing. This contract proved to be very effective based on the achieved results.

- Draft Protected Area Management Plan has been submitted to the Bank and comments have been received and sent to the Consultant company for consideration.

- Improvement works for community based lakeside vegetation pilot have not started yet. According to the plan the works for sage planting will take place in the same area burned by fires of August 2011.  Another situation of fires in the same area would spoil the sustainability of the related activities under the third component of the project. Final decision will be taken by the Ministry in collaboration with the WB.

Issues

- Planting of sage in the same area damaged by fires of August is risky, and this would spoil the sustainability of the related activities under the  third component of the project.

| NR | Contract (Description) | Type of Contract | No of Contracts | Procurement method | Review by Bank Prior/Post | Expected Contract signature date | Expected Contract completion date | status | issues |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Component One: Understanding and Management of Lake Shkodra Ecosystem |  |  |  |  |  |  |  |  |
| 1 | Project Coordinator | CS | 1 | Individual | Prior | 07/03/2008 | 06/30/2012 | completed |  |
| 2 | Operating Costs for the PIU | OC | - | - | - | Annual Plan |  | In process |  |
| 3 | Project Vehicle | G | 1 | Shopping | Prior | 02/13/2009 | 03/13/2009 | completed |  |
| 4 | Secretariat Staff Local Previous Secretary) | CS | 1 | Individual | Prior | 09/30/2008 | 11/30/2009 | completed |  |
|  | A). Joint Secretary | CS | 1 | Individual | Prior | 05/01/2010 | 12/31/2011 | completed |  |
| 5 | Assistant for Secretariat (Previous Assistant) | CS | 1 | Individual | Prior | 09/30/2008 | 11/30/2009 | completed |  |
| 6 | Operating Costs for Secretariat | OC | - | - | - | Annual Plan |  | In process |  |
| 7 | Operating Costs for SLC | OC | - | - | - | Annual Plan |  | In process |  |
| 8 | IT Equipments and Furniture for SLC Secretariat (*) | G | 2 | Shopping | Prior | 04/01/2009 | 05/30/2009 | completed |  |
| 9 | Laptop for the Project Coordinator | G | 1 | Shopping | Post | 07/30/2010 | 08/30/2010 | completed |  |
| 10 | Refurbishment of SLC Offices | CW | 1 | Shopping | Prior | 02/01/2009 | 02/28/2009 | completed |  |
| 11 | Refurbishment of the PIU office/space for the PC | CW | 1 | Shopping | Post | 02/22/2010 | 03/15/2010 | completed |  |
| 12 | Operating Costs for WGs | OC | - | - | - | Annual Plan |  | In process |  |
| 13 | Seminars, workshops, study tours for the joint structures and the PIU (*) | TR | - | “-“ | - | Annual Plan |  |  |  |
|  | A) Study tour with SLC | TR | 1 | - | - | Annual Plan |  |  |  |
|  | B) Study Tour with SLC | TR | 1 | - | - | Annual Plan |  | In process |  |
|  | C) Training on Wetland Management | TR | 1 | CQ | Prior | 02/01/2012 | 03/30/2011 | In process |  |
| 14 | Legal framework harmonization and integrating the role of the Commission into national legislation (*) | CS | 1 | CQ | Prior | 02/28/2012 | 07/30/2012 | Not started yet | SLC decided further discussion of Legal framework Review Recommendations (Point 22 Study 1) in the next meeting of the WG on Planning and Legal. Therefore TORs will be prepared after WG meeting and recommendation. |
| 15 | Public Awareness Campaign (*) | CS | 2 | CQ | Post | 09/01/2010 | 08/30/2012 |  |  |
|  | a). Public Awareness Campaign [1] (*) | CS | 1 | CQ | Post | 09/01/2010 | 09/30/2011 | completed |  |
|  | b). Public Awareness Campaign [2] (*) | CS | 1 | CQ | Post | 15/01/2012 | 07/30/2012 | TORs submitted to the Bank for No Objection |  |
| 16 | Joint fisheries stock assessment (*) | CS | 1 | CQ | Post | 01/15/2011 | 03/15/2012 | Draft final report to be received by December 15 | The Company requested time extension for submission of this report because they want to get data for some fish species which migrate at this time of the year. Without these data the report will not be complete. AL and MN PIUs have agreed to this no cost extension |
| 17 | Hardware for the Joint database | G | 1 | Shopping | Post | 01/15/2012 | 02/28/2012 | Not started yet | The company which is preparing Joint Database has suggested that we procure the hardware later on, before finalization of the contract. |
| 18 | Establish and maintain joint database (*) | CS | 1 | CQ | Post | 01/01/2011 | 01/30/2012 | Draft final report in process. | The company requested two months no cost extension |
| 19 | Lab equipment for targeted transboundary monitoring programs (*) | G | 1 | Shopping | Post | 09/30/2010 | 02/28/2011 | completed |  |
| 20 | Laboratory services for environmental monitoring | TS | 1 | Shopping | Prior | 02/28/2012 | 08/30/2012 | Not started yet |  |
| 21 | Expertise for social economic study (*) | CS | 1 | CQ | Prior | 11/15/2009 | 01/15/2011 | completed |  |
| 22 | Local Expertise for targeted studies identified by WGs (*) | CS | 6 |  | Post | 09/15/2010 | 06/30/2012 |  |  |
|  | Study no 1-Legal framework differences between Al and MN identified by WGs (*) | CS | 1 | individual | Post | 12/01/2010 | 09/01/2011 | completed |  |
|  | Study No 2- Investigation of the eutrophication level of the lake waters. | CS | 1 | CQ | Post | 10/30/2011 | 06/30/2012 | Contract not signed | Three applications received. Further decision pending from the MoEFWA. |
|  | Study No 3. Inventory of Tourist facilities and capacities in Lake area in Albania and Montenegro. | CS | 1 | Individual | Post | 04/01/2011 | 08/30/2011 | completed |  |
|  | Study No 4 | CS | 1 | Individual | Post | 10/30/2011 | 04/30/2012 | Not started yet | No proposals received from WG members |
|  | Study No 5 | CS | 1 | Individual | Post | 10/30/2011 | 03/30/2012 | Not started yet | No proposals received from WG members |
|  | Study No 6 | CS | 1 | Individual | Post | 10/30/2011 | 03/30/2012 | Not started yet | No proposals received from WG members |
| 23 | Assistance on Learning and capacity building on international cooperation on water basin management (regional expertise) (*) | CS | 1 | Individual | Post | 10/01/2011 | 10/31/2011 |  |  |
|  | - Field tip in Lake Skadar for IWC6 Participants | TS | 1 | Single source | prior | 10/13/2011 | 11/13/2011 | completed |  |
|  | - Printing of promotional materials | G | 1 | shopping | post | 10/13/2011 | 11/13/2011 | completed |  |
| 24 | Prepare Lake Wide Zoning and Management Plans | CS | 1 | CQ | Prior | 09/01/2010 | 01/30/2012 | Draft final report received and sent to the Bank | With request from the company the contract deadline extended for two months. |
|  | Component 2: Enhancing Sustainable use of Lake Ecosystem |  |  |  |  |  |  |  |  |
| 25 | Protection of spawning areas | CS | 1 | CQ | Post | 03/20/2011 | 06/30/2011 | completed |  |
| 26 | Expertise on Inventory Cultural Heritage | CS | 1 | Individual | Post | 07/08/2009 | 03/30/2010 | completed |  |
| 27 | Pilot renovation of cultural sites. | CW | 1 | NCB | Prior | 12/01/2011 | 05/30/2012 | Contract signed |  |
| 28 | Supervision of Construction works for pilot renovation of cultural sites | CS | 1 | Individual | Post | 12/01/2011 | 06/30/2012 | Contract signed |  |
| 29 | Different equipments for fishermen Management Organization Support | G | 4 | Shopping | Post | 09/30/2010 | 02/28/2011 | completed |  |
| 30 | Expertise for Fishermen Management Organization Support | CS |  |  |  |  |  |  |  |
|  | A) Business plan for the FMO | CS | 1 | Individual | Post | 09/02/2009 | 03/30/2010 | completed |  |
|  | B) Guide on fishery | CS | 1 | Individual | Post | 07/08/2009 | 12/30/2009 | completed |  |
|  | C) Survey on illegal fishing | CS | 1 | CQ | Post | 06/30/2010 | 07/30/2010 | completed |  |
| 31 | Survey on Illegal Fishing | CS | 1 | CQ | Post | 03/01/2011 | 05/30/2012 | Not started yet | To start in April 2012 |
| 32 | Equipment to enhance Lake protection Capacity | G | 3 | Shopping | Post | 09/30/2010 | 02/28/2011 | completed |  |
| 33 | Operating Costs for Lake Protection | OC | - | - | - | Annual Plan |  | In process |  |
| 34 | Operating costs for the FMO | OC | - | - | - | Annual Plan |  | In process |  |
|  | Component 3: Investment to protect water quality |  |  |  |  |  |  |  |  |
| 35 | Public Awareness Local | CS | 1 | CQ | Post | 08/15/2011 | 11/30/2011 | Contract Signed. Activities ongoing | Contract to close until end of December 2011 |
| 36 | Design Study of needs for restoring lake Tree groves | CS | 1 | Individual | Post | 10/08/2009 | 01/15/2010 | completed |  |
| 37 | Restoring lake tree groves | G | 1 | Shopping | Post | 08/15/2010 | 03/30/2011 | completed |  |
| 38 | ESIA for the stream bank erosion control | CS | 1 | CQ | Post | 11/15/2010 | 01/15/2011 | completed |  |
| 39 | Design for stream bank erosion control | CS | 1 | CQ | Post | 02/01/2011 | 03/01/2011 | completed |  |
| 40 | Stream bank Erosion control | CW | 1 | Shopping | Post | 09/30/2011 | 02/28/2012 | Contract signed |  |
| 41 | Supervision of construction works for stream bank erosion control | CS | 1 | Individual | Post | 09/30/2011 | 02/28/2012 | Contract signed |  |
| 42 | Architectural design for community based lakeside vegetation management pilot | CS | 1 | Individual | Post | 09/15/2010 | 05/30/2011 | completed |  |
| 4 | Improvement works for community based lakeside vegetation pilot | CW | 1 | Shopping | Post | 01/15/2012 | 04/30/2012 | Not started yet | Area of planting of sage is exactly in the area which was burned by fires in August 201. Therefore MoEFWA is requested from PIU to express its official attitude on this investment which seems risky. Needs to be discussed in the VC with the project director. |
| 43 | Equipment for community based lakeside vegetation management pilot | G | 1 | Shopping | Post | 01/15/2012 | 04/30/2012 | Not started yet |  |
| 44 | Procurement consultant | CS | 1 | Individual | Prior | 12/16/2008 | 09/30/2012 | Completed |  |
|  | TOTAL FOR ALBANIA |  |  |  |  |  |  |  |  |

- EXPENDITURES

| Disbursed until November 10 (USD) | Spent until November 30 (US$) | Committed/to be spent until end of December 2011 (USD) |
| --- | --- | --- |
| 1.077.095,61 | 980,000 | 140,000 |

NATIONAL ACTIVITIES-MONTENEGRO

Pilot renovation of cultural sites/visitor centers. “Open Plan Consulting” delivered the General Design which was approved by the Revision Committee on October 20, 2011 (Montenegrin language). Process of translation to the English language has been completed and General design has been submitted to  the PIU and the WB team on December 22, 2011. Extension of Contract duration until December 31, 2011 was proposed by the Consultant.

Works on migratory waterfowl monitoring stations.The ToR for project design was prepared by the NP Skadar Lake and approved by the WB team. The development of the General design is managed and financed by the National Park Skadar Lake and currently is in the final stage of development.

Vranjina WWTP construction –The Revision Comittee submitted the report on December 6, 2011 indicating the main issues the General Design needs to address before official approval.  The Revision Committee also concluded that costs of construction of the Constructed wetland as a WWTP for Vranjina will cost more than predicted in General design – in total 4.09 mil USD versus amount foreseen by the General design prepared by the Consultant- IK Consulting. (In total 2,72 mil USD).

This increasing cost may be a limiting factor for actual starting of construction works and this activity if the facts highlighted in the revision are found to be viable.

KAP Studies on waste inventory, site investigation, option analyses and feasibility studyThe amendment of  the ToR was proposed (regarding total/leaching sampling) and adopted on the 9th  KAP SC.  Site investigation report was submitted October 06, 2011 by SWECO and commented by the WB, KAP SC and KAP ITA. SWECO accepted to make more effort and sample analyses in order to improve Site investigation report. It is expected that SWECO will deliver updated Site investigation report after the additional research and analysis done, until end of December 2011.

KAP International Technical Adviser (ITA) –

The KAP ITA conducted two field visits in period: June- November 2011 (first on June 3 including 2+1 days, and the latter in October) Main topics covered during these visits were related to commenting on the SWECO deliverables, participating in the KAP SC and continuing capacity building of the Environmental Protection Agency and Ministry of Spatial Planning and Environment for implementation of Integrated Pollution and Prevention Control (IPPC) legislation.

| 1 | 2 | 3 | 3a | 4 | 5 | 6 | 7 | 7A | 8 | 8A | 9 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Contract (Description) | Type of contract | Amount financed by the GEF (million USD) | Negotiated amount | Number of Contract | Procurement Method | Review by Bank (Prior / Post) | Expected Contract signature Date | Exact Contract signature Date | Expected contract completion date in procurement plan | Expected contract completion date and status | Comment |
| Component 1 – Understanding and management of Lake Skadar Ecosystem |  |  |  |  |  |  |  |  |  |  |  |
| 1. Project Coordinator (local) | CS | 0.105 |  | 1 | Individual | Prior | 02/21/2009 |  | 09/30/2012 |  | Ongoing |
| 2. Operating cost for Project Coordination Team | OC | 0.0267 |  | - | - | - | Annual Plan |  |  |  | Annual Plan |
| 3. Office equipment (Combined with Line 18) | G | 0.0013 |  | 1 | Shopping | Prior | 02/23/2010 |  | 03/15/2010 |  | Completed |
| 4. Operating cost for the TSU (**) | OC | 0.048 |  | - | - | - | Annual Plan |  |  |  | Annual Plan |
| 5. Seminars, workshops, study tours for working groups (*) | TR | 0.040 |  | - | - | - | Annual Plan |  |  |  | Annual Plan |
| 6. Operating cost for working groups (*) | OC | 0.030 |  | - | - | - | Annual Plan |  |  |  | Annual Plan |
| 7. Development of Lake-wide Management Strategy, including Fishery Management Plans (*) | CS | 0.060 | 42.541,20 EUR | 1 | CQ | Post | 06/27/2011 | 06/27/2011 | 01/12/2011 | 01/12/2012-ongoing | Inception Report submitted on July 18, 2011 (according to the schedule) was cleared and Progress report is submitted for review |
| 8. Develop joint lake water/ecological Monitoring Program (*) | CS | 0.040 | 29.000 EUR | 1 | CQ | Prior | 11/05/2010 | 05/11/2011 | 09/15/201 | 09/15/2012 -completed | Completed |
| 9. TA for designing predictive hydrological model (*) | CS | 0.280 | 228.150, 00 EUR | 1 | QCBS | Prior | 11/15/2010 | 11/15/2010 | 09/30/2011 | 10/17/2011-ongoing | Completed |
| Component 2. Enhancing Sustainable use of Lake ecosystem |  |  |  |  |  |  |  |  |  |  |  |
| 10. Capacity building on tourism (local - first year contract financing only from GEF) | CS | 0.0125 | 8.400 EUR | 1 | Individual | Prior | 02/15/2010 | 02/15/2010 | 02/15/2011 | 02/15/2011 - completed | Completed |
| 11. Project Design for selected cultural monument | CS | 0.100 | 67.000 EUR | 1 | CQ | Prior | 06/21/2011 | 21/06/2011 | 08/30/2011 | 1/12/2011- ongoing | General design prepared and approved by the local authorities. Translation of documentation submitted for final NO to the WB team |
| 12. Works on migratory waterfowl monitoring stations | CW | 0.950 |  | 1 | Shopping | Prior | 12/30/2011 |  | 30/07/2012 | 30/07/2012 – not started yet | Not started – general design preparation in the final stage |
| 13. Capacity building for local communities cooperation (local – first year contract financing only from GEF) | CS | 0.0125 | 8.400 EUR | 1 | Individual | Prior | 02/15/2010 | 02/15/2010 | 02/15/2011 | 02/15/2011 - completed | Completed |
| 14. Different Equipment for fishermen organization support (fishing nets, etc) | G | 0.010 |  | 1 | Shopping | Post | 03/01/2011 |  | 05/01/2012 | 05/03/2012Not started yet | Will start after conclusion of PP line 15 |
| 15. Expertise on fishermen organization support | CS | 0.020 |  | 1 | Individual | Post | 10/01/2011 |  | 02/15/2012 | 04/15/2012 – not started yet | REOI published on December, 12, 2011 |
| 16. Motorized Small Boats (three types) for Enhancing Lake protection enforcement capacity | G | 0.090 | 68.570,00 eur | 2 | Shopping | Prior | 02/12/2010 | 02/09/2010 | 03/15/2010 | 03/15/2010 -completed | Completed |
| 17. Vehicles for Enhancing Lake protection enforcement capacity | G | 0.050 | 38.300.00 EUR | 2 | Shopping | Prior | 02/26/2010 | 23/02/2010 | 03/16/2010 | 03/15/2010 -completed | Completed |
| 18. Other equipment (binoculars, cameras, walkie-talkie, compass, etc) for Enhance Lake protection enforcement capacity | G | 0.010 | 12.237.65 EUR | 1 | Shopping | Prior | 02/23/2010 | 02/16/210 | 03/15/2010 | 03/15/2010 -completed | Completed |
| Component 3. Investment to protect water quality |  |  |  |  |  |  |  |  |  |  |  |
| 19. Vranjina WWTP building construction | CW | 0.440 |  | 1 | NCB | Prior | 12/31/2011 |  | 09/15/2012 | N/A –not started yet | Revision comate submitted report on December 6, 2011 indicating issues that General design needs to address before official approval. |
| 20. Study on waste inventory, site investigation, option analyses and feasibility study | CS | 0.880 | 795.000,00 EUR | 1 | QCBS | Prior | 11/15/2010 | 11/15/2010 | 05/15/2012 | 05/15/2012 - ongoing | Ongoing |
| 21. Environmental impact assessment | CS | 0.100 |  | 1 | CQ | Prior | 10/30/2011 |  | 05/15/2012 | 06/15/2012 – not started yet | REOI published on December, 12, 2011 |
| 22. International advisor KAP hazardous waste containment | CS | 0.103 |  | 1 | Individual | Prior | 11/01/2009 | 11/01/2011 | 11/01/2011 | 05/31/2012 -ongoing | Ongoing Two visits made. Extension contract amendment made on October 29 2011. New deadline May 31.2012. |

Contract for the Audit for 2010 signed on July 25, 2011 and concluded on 10/31.2011. 1.400.00 EUR from  national contribution/

- EXPENDITURES

| Disbursed until December 9 (USD) from January 1.2011 | Committed/to be spent until end of December 2011 (USD) |
| --- | --- |
| 535,200.00 | 584,290.00 |

ISSUES

Vranjina WWTP -Revision committee also concluded that costs of construction of the Constructed wetland as a WWTP for Vranjina will cost more than predicted in General design – in total 4.099.385,00 USD. This cost may be a strong limiting factor for actual starting of construction works and predicted activity.

PROJECT INDICATORS

|  |  | Data Collection and Reporting |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Outcome Indicators | Baseline | YR1 | YR2 | YR3 | YR4 | Frequency and Reports | Data Collection Instruments |  | Responsibility for Data Collection |
| Immediate and longer term threats to lake water quality and ecological system are reduced (S) Status of key transboundary indicators of Lake water quality and ecology maintained or improved (P) | Immediate threats: improperly stored hazardous waste in dumpsite affecting groundwater; pollution hotspots from untreated sewerage and soil erosion Long term threats: lack of institutional mechanisms (agreements, plans, agreements, regulations, incentives), data and analytical tools for protection and sustainable management of the lake and its resources Basic water quality indicators (BOD, Ammonia, Nitrite, Nitrate, CN, Zn, Pb,Cr,Hg, PAH, PCB) at multiple sampling sites all below detection or within Class 1A water quality parameters (see Annex 4); Status of selected transboundary indicators (algal concentrations, PAH/PCB and heavy metals in fish tissues, etc.) | See Intermediate Outcome Indicators for Components 1, 2 and 3 Basic water quality indicators indicators at baseline levels or better | Basic water quality indicators at baseline levels or better 72 water samples were tested for physico-chemical parameters. The temperature ranged from 14.1-28.2 °C and pH values ranged from 8.1 to 8.5. The DO values ranged from 6.7 - 9.7 mg\l . The results of conductivity changed from 215-232 μS\m. The average values of NH4-N ranged from 0.025-0.05 mg/L and the levels of NO3-N ranged from 0.18-0.27 mg/L. The average of fecal coli forms was from 101-102 cfu/100ml in Buna, Zogaj, and Livadhet during June, July, September and October 2010. According to the degree of total coli forms the water can be classified as good to moderate. The Shkodra lake water is good according to the European Community Standards. According to the physical-chemical analyses water quality of Lake Shkodra can be classified as good. According to the microbiological parameters analyzed and EU-Directive for surface waters (Quality of Bathing Water 76/160/EEC), Lake Shkodra results with slight pollution, fecal coli forms (100-2000 cfu/100ml) and total coli forms (100-500 cfu/100ml). In most cases G-values of the EU-directive on bathing waters for total coli forms and fecal coli forms were met. The cleanest point resulted was Middle lake and the most problematic point regarding both chemical and microbiological parameters was Buna, because of the discharging of sewages of the municipality, which has an impact to the water quality in particular areas of river Buna. | Basic water quality indicators at baseline levels or better According to the 2010 MNE EPA State of Environment Report the water quality of of Skadar Lake is very good (Water Quality index 85) and belongs to the A2 class according to the national classification. Only few locations registered excess of parameters for A2 class (mainly: Nitrates, BPK, temperature) (see Table 1 and 2 below with specific values for selected indicators). | Basic water quality indicators at baseline levels or better | Annual or bi-annual | Water quality monitoring and analysis equipment |  | METP/MEFWA; Designated national scientific institutions |
| Development and water use decisions/actions are guided by bilateral objectives, agreements and structures (P) | 2003 MOU signed; Draft Bilateral Agreement signed before project negotiations No bilateral structures in place | Skadar-Shkodra Lake Commissionand 4 Working Groups formally established; 4 WGs established: WG on Planning and legal; WG on Water Management; WG on Monitoring and research; WG on Communication, Outreach and Tourism Promotion Working Groups complete vision statements and draft work plans WGs have discussed and given their input to the preparation of Terms of Reference and review of several joint documents such as the Social Economic Assessment, etc. | Working Groups submit to SLC drafts of bilateral plans called for in SAP (tourism, communications/ outreach, monitoring) The WGs discussed Terms of Reference, reviewed reports and gave their input to several joint bilateral documents: Social Economic Assessment, Predictive Hydrological Model, Legal Framework Review, Joint Database, Fish Stock Assessment etc | SLC approval of bilateral plans Specific policy and action measures for bilateral adoption identified On the fourth SLC meeting decision was made to prepare MoU between respective ALB and MNE institutions regarding use of the PHM developed in the framework of the project. 30% of costs of Skadar-Shkodra Lake Commissioncovered by Government Budgets 100% of the SLC costs agreed to be covered by Government budgets in 2012 | SAP updated based on bilateral plans Bilateral Agreement updated based on Working Group/SLC recommendations 50% of SLC costs covered by govt. budgets | Semi-annual | Project progress reports; public Annual Reports of SLC; SLC website |  | MTEP/MEFWA; SLC Joint Secretariat; |
| Intermediate Outcome Indicators |  |  |  |  |  |  |  |  |  |
| Component 1 Capacity Building for Improved Understanding and Joint Management of the Lake |  |  |  |  |  |  |  |  |  |
| SLC and Secretariat, lake-wide database and Working Groups are in place and operating; costs of continuing operation and participation are included in Governments’ budgets at project’s close (P) | None of these structures in place | SLC and Working Groups established; and first meetings held for all 4 WGs established: WG on Planning and legal; WG on Water Management; WG on Monitoring and research; WG on Communication, Outreach and Tourism Promotion. First meetings held Secretariat and Project Coordinators recruited; offices equipped and operational Secretariat and Project Coordinators recruited; offices equipped and operational Equipment/TA for developing database procured Equipments will be procured after preparation of the database | 2 meetings of SLC held, minutes/conclusions publicly available At least one bilateral activity identified and under implementation for each Working Group Activities identified: Legal Framework review, Joint Public Awareness campaign, Identification of Eutrophication level of the lake waters, establishment o the predictive hydrological model. Database operational; historical data uploaded TORs prepared | 2 meetings of SLC held, minutes/conclusions publicly available. Fourth meeting was held on October 07, 2011 One bilateral activity completed for each Working Group Legal Framework review, First Contract of the Joint Public Awareness campaign, completed Database kept updated with input from both countries Database in finalization steps. Documents and data uploaded; expected to be finalized by (DATE?) | Both Governments’ budgets fully support SLC/ Secretariat/WG Operating Costs. Database kept updated with input from both countries | Annual | Project progress reports; SLC website SLC website |  | SLC Joint Secretariat |
| Predictive hydrological model of Lake Skadar-Shkoder completed and being used to analyze likely impacts of policies and proposed investment. (P) | No model exists | TORs for development of model and consultant selection completed TORs for development of model and consultant selection completed | Draft hydrological model submitted to SLC, distributed to appropriate stakeholders for review and comment First Reports on hydrological model submitted to SLC and relevant stakeholders | Final hydrological model completed; outreach/dissemination under way Predictive Hydrological Model completed. Installation agreed in SLC to be done in Montenegro | Hydrological model used to analyze impacts of at least 1 proposed water-related development in lake basin |  | Report drafts and commentaries |  | MTEP; Research & Monitoring Working Group; SLC Secretariat |
| Lake management plan completed and actions taken to legally operationalize the plan. (P) | No lake management plan exists | Bilateral Working Group approves TOR for plan preparation | Draft Lake management plan completed | Lake mgt plan approved by BLCM following stakeholder consultations; identification of measures needed to legally effect the plan in both countries The development of Joint Lake Management Strategy including National Fishery Management Plans for each country is on-going. Inception Report submitted on July 18, 2011 was approved and Progress report is submitted in line with the project Work Plan and activity schedule, and covers the period from 12.07.-10.10.2011 | Actions taken to legally effect the Lake wide management plan. |  | Project progress reports; SLC website |  | MTEP/MEFWA; SLC Joint Secretariat and Planning Working Group |
| Component 2: Promoting Sustainable Use of the Lake |  |  |  |  |  |  |  |  |  |
| Targeted tourism infrastructure renovations/construction Completed. (S) | Minimal tourism infrastructure exists | Designs completed for hiking trails, eco-camp, cultural sites) | 25% of rehabilitation/construction work completed In Montenegro: Agreement with the European delegation in Montenegro and Ministry of Culture of Montenegro for future reconstruction of the Besac fortress achieved TORs for development of general design for reconstruction of Besac fortress and consultant selection completed. | 75% of work completed. In Albania restoration works have started on December 01, 2011 and are foreseen to be completed by May 30, 2012. In Montenegro,general design for reconstruction of the Besac has been completed according to the national legislation and pending for final NO from the WB team. Based on general design it is expected that European Delegation in the MNE will finance restoration works in the amount of 0.48 mil Euro in the first half of 2012. | 100% of work completed | Annual | Project progress reports |  | MTEP/MEFWA; joint SLC Secretariat |
| Reduction in numbers of fishermen using illegal fishing methods (S) | Estimated 350 unlicensed fishermen (43% of total); 814 cases of illegal methods observed during 1 week survey | In Montenegro 58 % illegal fisherman’s registered (No of issued licenses VS No of processed infringements + felonies ) For the 2008 year 280 illegal methods registered during course of one year | Unlicensed fishermen not exceeding 30% of total In Montenegro: 21 % illegal fisherman’s registered (No of issued licenses VS No of processed infringements + felonies ) In Albania number of illegal fishermen decreased from 44% to 38% Not more than 400 cases of illegal methods observed during 1 week survey period In MN for the 2009 year 99 illegal methods registered during course one year In Albania 576 cases of illegal fishing were observed during a one week survey in 2010 | In Montenegro 17,7 % illegal fisherman’s registered (No of issued licenses versus no of processed infringements + felonies ) In Albania number of illegal fishermen observed from June-December is 120 or 27% (450 legal, 120 illegal). In Montenegro there were 103 illegal methods registered during course of one year (2010) In Albania 8 cases of illegal fishing were observed during banning period in April-May 2011 and at least 30 cases of illegal fishing were observed in the period June-December 2011 ( | Unlicensed fishermen not exceeding 20% of total Not more than 100 cases of illegal methods observed during 1 week survey period | Every 2 years | Field survey (repeat of baseline survey undertaken during preparation) |  | MEFWA, SLMNR Authority |
| Increased local understanding of and engagement in sustainable tourism and natural resource management (P) | TBD: survey to be undertaken during first year of project | Completion of survey, providing indicators, baseline measures and targets for awareness and engagement Social Economic Survey initiated | Social Economic completed |  | Awareness and engagement indicators reach at least 70% of target levels | Survey carried out in Year 1; repeated in Year 3 or 4 | Socio-economic survey |  | MTEP/MEFWA |
| Component 3: Catalyze Pollution Reduction Investments |  |  |  |  |  |  |  |  |  |
| Government of Montenegro/KAP owners (Rusal) agreement on preferred solution and joint action plan for containment/disposal of hazardous waste dump site at KAP site (P) | Inadequate, outdated information on nature and quantity of legacy waste and site conditions; no basis for analysis of options; no action plan or agreement on way forward | Aluminum Plant Technical Advisor to Government in place KAP ITA consultant selection completed and contracted; his work is on-going until May 31,2012 KAP Project Steering Committee Established KAP Project Steering Committee Established with 11 members and meeting held regularly Waste categorization study completed TORs for Options Analysis/ feasibility study/preliminary design and for EIA completed TORs for Options Analysis/ Feasibility Study/Preliminary design prepared. | Options analysis completed Feasibility study and EIA initiated TORs for development of KAP feasibility study and consultant selection completed. - Health and safety plan (HSP) and Dumpsite and subsoil investigations at the site completed as a basis for the site investigation report and Option analyses. | Feasibility study completed; Draft Site investigation report submitted and Best practicable environmental options report and Feasibility study expected to be finalized until March 2012. TORs for development of KAP EIA study completed and REoI published. GoM/KAP owners agree on preferred solution Preliminary design work initiated Draft Agreement on action plan, including funding, implementation responsibilities and modalities Government of Montenegro will receive a loan from the International Bank for Reconstruction and Development (IBRD), proposed to reduce the environmental and public risks of selected industrial waste disposal sites through investments in environmental control measures and infrastructure for management and disposal of industrial waste including KAP hazardous waste dump site. Proposed project is in preparation phase and will build on the findings from the Feasibility study and EIA done under LSIEMP. | Preliminary design and EIA completed Final agreement on action plan and financing, approved by both Rusal and GoM | Regular | Project progress reports |  | MTEP; KAP/Rusal |
| Sewage collection and wastewater treatment system established at Vranjina village (Montenegro) (S) | Only sanitation in place is largely non-functional septic tanks. Visible pollution at outlets TORs for Feasibility study and environmental review for sewerage/WWT at Vranjina. | Vranjina: baseline water quality parameters recorded at pilot sites; construction of sewerage collection system initiated | Vranjina: sewerage collection system completed TORs for General design for construction of the WWTP constructed wetland and consultant selection completed. | Vranjina: Construction of WWT system completed (anticipated to be constructed wetland) General design for construction of the WWTP Constructed Wetland finished. Exploring possibilities for financing the works in progress | Vranjina: WWT system used as demonstration site | Regular | Project progress reports |  | MTEP, Podgorica Municipality, MEFWA, restaurant owners |
| Area of water buffer vegetation restored in pilot areas to reduce sedimentation and runoff. (S) | 2 degraded sites for restoration sites identified; no data on vegetation cover | Indicators, baseline and targets for vegetation cover identified; TORs for contracts prepared | Contracts awarded and restoration work initiated | 50% of restoration work completed 60% completed | 100% of restoration work completed | Regular | Project Progress Reports |  | MEFWA |

Table1. Values for basic water quality parameters in the Skadar Lake (MNE State of Environment Report, 2010)

| Parameter | units | 1990-19951 | July 20051 | July 20102 |
| --- | --- | --- | --- | --- |
| Turbidity NTU | NTU | 1,6 | 3 | <1 |
| Ph | - | 8,22 | 8,25 | 8,0-8,2 |
| HCO3 | mg/l | 195,2 | - | 177-211 |
| Dissolved oxigen (surface water) | mg/l | 7-12 | 12,2 | 12,7-14,5 |
| Dissolved salts Dry residue Conductivity | mg/l µS/cm | 140-160 205 | 135-170 237 | 151-183 253-308 |
| Phosphates (PO4) | mg/l | 0,005 | <0,01 | 0,01-0,04 |
| Nitrates (NO3) Nitrites (NO2) | mg/l mg/l | 0,45 0,004 | 2,9 0,006 | <0,01-1,25 0,002-0,008 |

Sources:

1 TDA LSIEMP

2 Report on water quality in Skadar Lake in the condition of the 2010 floods – HMI Montenegro, 2010.  Values are given from 7 sampling locations in the Skadar Lake

Table 2. Concentrations of  PCBs and OCPs in  water from lake Shkodra (ng/L) (Source: Laboratory of Ecotoxicology, University of Shkodra, December 2011)

| Compounds | Sample 1 | Sample 2 | Sample 3 | Sample 4 | Sample 5 | Sample 6 |
| --- | --- | --- | --- | --- | --- | --- |
| α-HCH | 51.8 | 39.8 | 39.7 | 26.1 | 50.7 | 46.2 |
| Hexachlorobenzene | 305 | 58.2 | 117 | 148.9 | 242 | 234 |
| β-HCH | 42.3 | 14.5 | 31.1 | 55.4 | 54.9 | 16.56 |
| Lindane | 529 | 3695 | 433 | 751 | 447 | 342 |
| Heptachlor | 8.25 | 5.95 | 8.23 | 9.80 | 9.26 | 38.1 |
| 2,4-DDE | 29.2 | 20.2 | 20.1 | 48.5 | 22.1 | 69.1 |
| 4,4-DDE | 10.3 | 1.61 | 6.32 | 48.2 | 10.5 | 106.3 |
| p-p'-DDD | 20.1 | 3.18 | 17.8 | 83.1 | 14.7 | 9.98 |
| p-p'-DDT | 6.66 | 2.52 | 4.80 | 19.2 | 4.84 | 1.80 |
| Methoxychlor | 1091 | 76.4 | 7663 | 796 | 9980 | 298 |
| PCB-28 | 147 | 27.1 | 55.5 | 57.5 | 63.9 | 18.9 |
| PCB-52 | nd | nd | nd | nd | nd | nd |
| PCB-101 | 230 | 8.91 | 8.6 | 7.08 | 8.67 | 19.7 |
| PCB-118 | 13.5 | 12.6 | 12.2 | 7.58 | 7.53 | 8.02 |
| PCB-153 | 10.9 | 2.34 | 11.1 | 15.18 | 4.98 | 1.31 |
| PCB-138 | 4.1 | 2.1 | 3.6 | 7.28 | 2.06 | 1,05 |
| PCB-180 | nd | nd | nd | nd | nd | nd |